THE CONFEDERATED TRIBES OF THE WARM SPRINGS RESERVATION OF OREGON

Branch of Natural Resources

P.0. Box C, Warm Springs, Oregon 97761

Phone (541) 553-2002/2003

Fax (541) 553-1994

To: 	The Independent Science Review Panel (ISRP) for the Northwest Power and Planning 	Council, Eric Loudenslager, Chair

From:  Brad Houslet, Fisheries Program Manager, and

Jens Lovtang, Fisheries Management Supervisor

Confederated Tribes of Warm Springs

Branch of Natural Resources 	Fisheries Department

Re: 	CTWSRO Response to: Final Review of the Confederated Tribes of the Warm Springs 	Reservation’s Fish Accord Proposal, Project, Natural Production Monitoring and 	Management (#2008-311-00)

SUMMARY

The Confederated Tribes of the Warm Springs Reservation of Oregon (CTWSRO) appreciates the constructive criticisms and comments on the latest draft of the Fish Accord Proposal for project 200-311-00, Natural Production Monitoring and Management (June 16, 2010).

The IRSP requested a more comprehensive presentation of data that has been collected by the CTWSRO in the past 30 years.  In response, we expanded the technical and scientific background section to include this information.

We expanded the description of protocols on life cycle monitoring of naturally produced anadromous steelhead and spring Chinook salmon in Reservation streams and focus on five objectives:  1) adult escapement, (2) spawning ground (redd) surveys, (3) summer snorkeling rearing surveys, (4) juvenile outmigration estimates, and (5) PIT tagging juvenile outmigrants.  The description of each of these objectives has been expanded to include sampling design, data collection protocols, and statistical analyses.

Some objectives have also been removed from the proposal.  We agree that genetic tissue sampling of steelhead and rainbow trout is inappropriate at this time.  Instream incubation of steelhead eggs was removed from the previous version of the proposal.  We also removed specific methods for fisheries management, including harvest estimates.  All management activities are now included in Goal (2).  Although some of the information used to manage fish resources in the Deschutes River Subbasin (Goal 2) will be collected through work conducted as part of this proposal, the weighing of that information by co-managers, and the actual management decisions are not part of this proposal.  These management activities are policy in nature rather than technical.  We therefore limit our description to a general overview of management activities.

Note – ISRP comments are shown in italicized text.  All responses provided by the Warm Spring Tribe are in normal text.

SPECIFIC RESPONSES

Background

This proposal was originally submitted as two proposals to the ISRP for review in November 2008.  One of the proposals was for spring Chinook, and the other was for steelhead.  On December, 12, 2008, we requested additional information before we could determine if the proposals met scientific criteria.  Specifically, the ISRP found that the proposals did not contain sufficient information regarding details on the methods for each of the objectives, how the projects would inform management actions, and the benefits to the targeted fish populations.

The decision was made after the initial round of ISRP comments to combine the Chinook and Steelhead projects into one Natural Production Project because many of the activities were combined (e.g. outmigrant trapping and snorkeling) or similar (e.g. redd surveys).  The current version of the proposal supplies the necessary information on methods and protocols.

For both projects, the ISRP noted that the levels of culture and release of fish for testing supplementation appeared to be of sufficient scale to warrant a Three-Step Review and compliance with Northwest Power and Conservation Council Artificial Production Review policies, and possibly development of an HGMP.

We understand that the narrative must describe in detail the specific activities that will be undertaken as part of this project.  Therefore, the scope of the project has been greatly focused.  The aspects of the original proposal(s) that would have required a Three-Step Review and/or an HGMP (the incubation of steelhead eggs) have been removed.

ISRP Recommendation

The ISRP specifies recommendations for each of the objectives under the project’s goals.

Goal 1.  Continue and improve annual life stage monitoring of wild spring Chinook salmon and steelhead in the Warm Springs River Basin and Shitike Creek.

Objective A)  Juvenile Outmigration Monitoring – Response Requested.  This task requires further detail as well as attention to methodological problems.  See details below.

This part of the proposal requires further detail as well as attention to methodological problems.  For example, the ISRP cautions against anesthetizing and/or PIT-tagging all captured smolts.  Separate marking and recapture locations are preferred for smolt estimation with rotary screw traps.  Similarly, justification of the number of fish to be handled to estimate trap efficiency should be provided.  The level of stratification proposed for species, sizes, and age classes will likely provide spurious results – recapture rates will likely be too low for this level of stratification.  Evaluation of sample size requirements in advance is highly recommended and should be available for reviewers.

We will implement protocols as described in Carlson et al. (1998) and the ISEMP protocols (Tussing 2009) to estimate populations of outmigrating salmonids using outmigrant traps.  We also recognize the limitations of attempting to estimate outmigration populations with small sample sizes, and have included a discussion regarding sample size determination.

The proposal would also be improved by provision of a statistical basis for numbers of fish to be PIT tagged – at present it appears an opportunistic tagging program is proposed, which is not scientifically defensible.

The PIT tagging section has been expanded to include more detail, including a list of specific objectives and sample size precision.

Objective B)  Collect tissue samples for genetic analysis of O. mykiss in the Warm Springs River drainage – Does Not Meet Review Criteria.  The use of genetic analysis to identify individual resident versus anadromous smolts has yet to be demonstrated, and most existing data from other subbasins would suggest this differentiation unlikely.

This objective has been removed from the proposal.  After review with geneticists and other basin managers, we agree that the goals of the genetic tissue sampling as proposed are unrealistic.

Objective C)  Summer rearing snorkel surveys – Response Requested.  Methods for snorkeling are very general, and it is not clear if standard methods are being followed.  Statistical methods are not adequately explained, and it is not clear how presence or absence data in the lower Warm Springs River will tie in with “quantitative” snorkeling upstream.  The proponents also need to provide information on methods for obtaining presence or absence data in the lower reaches.  See details below.

The proponents state that a selected number of pools will be repeated as index sites in day and night dives each year for direct annual comparison.  How will the required number of pools to be selected be determined?  That is, how will the sampling effort be established to ensure meaningful comparisons among years?  Justification for selecting “70 pools and 25 riffle segments in 13 stream reaches” for sampling should be provided to ensure this sampling effort is appropriate for study purposes.  Once population estimates are created, specifically what “statistical tests” will be performed to investigate the data?

We will implement standardized protocols similar to other programs in the Interior Columbia River Basin.  We will use GRTS site selection protocol to choose our sample sites.  Data collection protocols will be adapted from Thurow (1994) and Murdoch and Nelle (2008), and a second method of fish collection (electrofishing or mark/recapture) will be used to calibrate accuracy of underwater counts (Hankin and Reeves 1988, Dollof et al. 1993).  Methods are expanded to include further detail.

Objective D)  Spawning ground (redd) surveys – Response Requested.  Statistical methods for redd survey data are not given in detail, and the proponent should provide justification that the effort will provide adequate precision.  Increasing prespawn mortality for Chinook is a cause for concern and should receive more attention with respect to climate change.  The ISRP also noted the methods used to calculate prespawn mortality need to be improved – “Prespawning mortality is estimated for populations in the Warm Springs River Basin by fish per redd ratios.  These ratios are dividing the total number of fish passed at the WSNFH by the number of redds counted in the upper basin.”  The proponents should confirm that fish that did not build a redd in the upper Basin actually died in these reaches and did not spawn downstream.  Direct counts of dead unspawned fish might be a better metric.

Redd survey methodologies are expanded and explained.  A rotating survey panel will be used to survey non-index reaches, resulting in a full census of all habitat every five years.  Redd surveys will not be used for adult escapement estimation.  These surveys serve only as an annual index of escapement and we are aware that caution must be used when relying upon redd counts collected under our methodologies for management purposes.

Accurate calculation of prespawning mortality in the Warm Springs River basin is difficult, primarily because most of the over summer holding habitat (approximately Rkms 17 to 47 of the Warm Springs River) is at the bottom of a 1000+ foot deep desert canyon with limited road access.  The lower five miles of Mill and lower seven miles Beaver Creeks are similar – deep canyons with poor access.  Accessing these reaches to conduct either redd surveys or carcass surveys is difficult and potentially dangerous.  The majority of the spawning index reaches are upstream of these canyons.  We propose a rotating panel study design that will cover 100% of the habitat available habitat over five years' time by surveying approximately 20% of the “non-index” reaches annually.  We also propose to survey the Warm Spring Canyon twice a year, in July and August, to look for prespawn mortalities.

Carcass surveys are conducted by the CTWSRO on the Warm Springs River and its tributaries in during redd surveys (something that we neglected to mention in the proposal), but it has been determined to be unreliable method of determining prespawning mortality because we find few of them.  On average, 70 carcasses are examined annually (range 16 to 310), which represent only about 6% of the average total run.  In 2001, the CTWRSO located 310 carcasses (our highest count), which represented less than 13% of the known escapement of spring Chinook salmon past the WSNFH.  Carcasses disappear from the river soon after spawning, either because they drift into inaccessible habitat in the above mentioned canyons, or they are removed before or after spawning and consumed by the many “critters” that inhabit the east side of the cascade mountains.

We feel that using the index reach counts combined with the known escapement of fish past the WSNFH is the best option we have available to estimate the relative annual differences in pre-spawning mortality and spawning success.  We understand that due to the potentially incomplete census of redd counts that it will be an over-representation of the true percentage of pre-spawning mortality.  But, assuming the redd surveys are accounting for a relatively consistent proportion of the true number of redds, it does provide a relative measure of annual variation in spawning success.

Objective E)  Enumerate adult escapement into Shitike Creek and the Warm Springs River – Response Requested.  The proposal requires inclusion of statistical methods as well as information on any plans to improve weirs so they work at high water.  Are electronic methods proposed?  The data gap during high water for steelhead enumeration may make this objective difficult to reach.

The CTWSRO proposes to solicit a contract with an experienced consultant to design, construct, and install a weir in Shitike Creek.  A discussion of the methodology of estimating escapement is included.  Adult escapement in the Warm Springs River is conducted by the USFWS at the WSNFH.

Objective F)  Estimate harvest of Chinook salmon and Steelhead in the Deschutes Basin – Does not meet review criteria.  Creel census methods are not described in sufficient detail to evaluate this objective.  The proponents should coordinate with CRITFC biologists doing similar work in Zone 6 in the lower Columbia River (Proposal 2008-502-00).  Some of the same fishing methods are being used.

Harvest / creel surveys are an important part of spring Chinook and steelhead monitoring in the Deschutes Basin, and will continue for the foreseeable future.  Although these surveys are discussed in the management section, they are funded through a different source; therefore, they will not be included in the work objectives for this specific project.

Our creel surveys are complementary to those implemented annually by ODFW.

Goal 2.  Provide management and co-management direction of the fisheries resources in the Deschutes River Basin

Objective A)  Cooperate in Deschutes River Basin Fisheries Management Activities – Response Requested.  The ISRP concluded this objective has a strong policy element.  Protocols for monitoring and evaluating the effectiveness of management programs should be specified.  Development of indicators may be a worthwhile approach (see the ISRP report, Input on Evaluation of Regional Coordination Projects, ISRP 2007-14).  The specific management tasks (i.e., setting harvest seasons and creel limits), effort for each task, and how the data from Goal 1 are to be used, and measures to determine if the data are sufficient, would be required to evaluate this objective.

A more detailed discussion of CTWSRO involvement in Deschutes River Fisheries management is included.  Although management decisions rely in part on information collected as part of the proposed project, actual management decisions are not part of this proposal.  We therefore limit our description to a general overview of management activities.

Objective B)  Provide co- management and assistance with fish handling at the Warm Springs National Fish Hatchery – No Recommendation.  The ISRP concluded this objective also has a strong policy element.  An exception is the use of WSNFH as a production facility as well as “a tool to improve and enhance runs of wild steelhead and spring Chinook” which is a science issue.  The ISRP was unsure if evaluation of this use is within the scope of this review and hence did not comment on this sub-objective.

Supplementation test

There was little or no mention of this component that appears to have been removed from the original proposal, but the test appears to be a primary justification for the proposed work.  A linkage or discussion of the relevance of the Chinook hatchery program or the steelhead hatchery strays to natural production monitoring and management should be.  Given that it seems no hatchery fish are allowed above the weir at the Warm Springs River National Fish Hatchery (page 15), perhaps impacts of hatchery fish on natural production are less of an issue.  The proposal would be improved by providing important details such as the release sites for hatchery smolts.

This component has been removed from the proposal as the CTWSRO is no longer performing this activity.  The CTWSRO performed this task in 2009, but did not in 2010, and will not in the foreseeable future.  The eggs in question were taken from air spawned wild steelhead, which were captured at the WSNFH fish ladder.  Those fish were taken as part of CRITFC’s Kelt reconditioning Project (BPA Project 2007-0401-00).  The eggs were fertilized and incubated instream in part due to negotiations with our Tribal Fish and Wildlife Committee.  They requested that, rather than throw the eggs away, we use instream incubation so as not to lose all the potential production.  The Kelt Reconditioning Project was discontinued in Warm Springs in 2010, and therefore we will no longer have eggs available for this activity.

All hatchery smolts reared at the WSNFH are released directly from hatchery ponds into the Warm Springs River.  The impacts of hatchery fish upstream above the WSNFH are limited to the potential genetic introgression of the few hatchery fish that are unintentionally passed upstream via the volitional bypass system, which detects coded wire tags in hatchery fish and diverts those into a pond without upstream access.  Those fish without CWTs (including those hatchery fish that have lost theirs) are allowed to pass upstream without being handled.  Video monitoring is used to track the proportion of ad-clipped and unmarked wild fish passing upstream.  Tribal and USFWS policy dictates that no more than 10% of the total upstream escapement may be hatchery origin fish (CTWSRO and USFWS 2007).

Relevance to management actions and benefit to fish

While the proponents did provide a basic presentation of data on the Chinook and steelhead adult returns since 1975 and 1977, respectively, additional analyses or discussion of results, other than mention that the specific causes for these variations and recent decline are unknown, is necessary.  Exploration of these data is necessary to demonstrate the use of such information for management purposes.  Inspection of the adult data raises the suspicion that trends in abundance mimic ocean conditions, and this needs to be explored.  There is also a need to split the life stage analyses into freshwater (adult-smolt) and ocean (smolt-adult) components to fully interpret the recruitment information.  This also applies to using jacks to predict subsequent adult returns, in good versus poor years of returns.  Additionally, smolt estimation techniques from RST should be further explored. Peterson M-R is not effective for this (Mäntyniemi and Romakkaniemi 2002).  In addition, adequate information or results and trends from redd surveys, smolt yield estimation, snorkel or electrofishing surveys should be provided from past years of data collection.  Harvest results were also not presented.  Adequate justification was also lacking to provide management advice.  A decision plan should be provided describing target reference points for decisions such as adult recruits per spawner or smolt recruits per spawner.  There was emphasis that continued collection of these data allows for comparison of multiple life stages for each brood year, such as potential egg deposition, egg-to-fry-to-smolt survival, recruits per spawner, and smolt-to-adult returns.  However, the ISRP cannot evaluate if the data actually enable comparisons, since the metrics were not provided.

We have expanded the amount of background and historical data in the proposal, which includes such information as estimates of recruits per spawner and smolt-to-adult returns.  We also appreciate the comment that we should not claim to produce and evaluate metrics for which we have incomplete or inadequate data, such as potential egg deposition and egg-to-fry-to-smolt survival.

On page 8, run size objectives were provided.  How were these derived?  The proposal would be improved by a description of the process the proponents used to determine these values and, furthermore, provide the list of management actions that are triggered at varying levels of return, indicating targets and limits.

These run size objective are taken directly from the Lower Deschutes River Management Plan (LDRMP) (NPCC 2005).  To determine biological objectives, the subbasin planners used “… the Ecosystem Diagnosis and Treatment (EDT) and Qualitative Habitat Assessment (QHA) analyses to compare focal fish species needs during different life stages with the conditions existing in various stream reaches.  The analyses integrated knowledge of the environmental attributes critical to fish with species-specific environmental requirements, reproductive potential and life history strategies to predict the performance of a population subject to current, historic or hypothetical environmental conditions (NPCC 2005.)”

The development of the LDRMP was a multi-year effort amongst several agencies, including the CTWSRO.  The biological objectives were agreed to when all parties signed off on the document, and are the goals that the co-managers are working towards.  However, we have removed the LDRMP numerical biological objectives from the narrative in favor of a more general description of sub basin planning goals.

Although efforts are being made to assess habitat restoration, identify areas of high or low productivity, and provide information on annual trends of productivity, the proposal would be improved by information on how this is actually going to be done.

Although personnel from this project may work with the CTWSRO Deschutes River Restoration Project (DRRP) in their efforts at habitat restoration, the specifics regarding the methodologies for assessing the efficacy of those efforts are part of the DRRP and are beyond the scope of this project, and will therefore not be discussed in this proposal.

________________________________________

w:\mf\ww\moa 2008-2010\three tribes\submittals\nov4 accord 11 narratives\200831100\2011\040111 isrp response.doc