## Sheet 1
F&W Program Screens - DRAFT version August 10, 2017
Following is the list of non-recurring maintenance priority needs associated with the F&W Program screens for Fiscal Year 2018, including estimates for FY2019 and 2020. This information was received from 5 of the Programs 14 screen projects. The priority of the sites are as received from the managers. Staff aligned the priorities to the Fiscal Years for planning purposes only. FY 2018 actions are dependent on review and confirmation by Bonneville engineers by the end of October 2017. Allocations of funds from FY 2018 cost savings is $150,000 Final budget allocations of the $150,000 will be based on that assessment and prioritization. In addition, permitting and environmental compliance also needs to be confirmed.
Manager/Sponsor (number of screens) | Site | Estimated Cost by Fiscal Year |  |  | Comment
|  | 2018 | 2019 | 2020
Idaho (#255) | L-03AO | 100000 |  |  | Older 45 degree screen, relocate new screen and bypass. River has moved and screen is not functional.
| L-06 |  | 7500 |  | new bypass. Add debris rack and bypass replacement
| L-08 |  |  | 60000 | new screen. Older 45° screen.
WDFW (#42) | Snipes and Allen | 100000 |  |  | WDFW proposes to replace the screen material with new fish-friendly perforated plate. In addition, structural fabrication needs for the frames (e.g., original high build epoxy coating is experiencing failure) will be completed during renovations.
| Naches-Cowiche |  | 100000 |  | WDFW proposes to replace the screen material with new fish-friendly perforated plate. In addition, complete refurbish of OU gate , gantry and lighting is needed.
ODFW (#572) | Beech Cr. NO. 7 | 40000 |  |  | Update Walkways (2); Needs Guards for paddlewheel/Driveline; Gantry replacement; modify bypass trash rack; Sand Blast and paint components or replacement; bearing replacements; seals
| John Day River NO. 06 |  | 20000 |  | Update Walkways (2); Needs Guards for paddlewheel/Driveline; Gantry replacement; modify bypass trash rack; update paddlewheel; Sand Blast and paint components; bearing replacements; seals
| Westside Diversion |  |  | 10000 | Sand and paint gantries, replace walkways and handrails to meet OSHA standards. Brace Concrete wall and backfill with gravel to prevent freezing weather from moving concrete strait wall. Replace trash Racks.
MFWP (#5) | Grave Creek | 60000 |  |  | Replace screen, bypass and headgate severely damaged by tree fall in 2016. Currently the screen is non-functional.
| Libby |  | 25000 |  | armoring/protecting headgate
| Deep Phase 2 |  |  | 15000 | Infrastructure repair
Westland Irrigation District (#6) | West Extension Irrigation District (WEID) diversion located at Threemile Dam | 281316 |  |  | Refurbish 4 (9' diameter x 12' length)screens to meet NMFS criteria. Current screen material was grandfathered in.
Total Requested by Managers |  | 581316 | 152500 | 85000
Recommended FY 2018 Placeholder |  | 150000