## Cover_page
Appendix B: Future Cost Summaries for Summer/Fall and Spring Chinook Programs

## APP_B_Future_Cost_Summ_Fall
Appendix B: Future Cost Summaries for Summer/ Fall Chinook
Costs Expended to Date
Description | Month | [11 empty] | Quarter |  |  |  | FY 2003
| January | February | March | April | May | June | July | August | September | October | November | December | Q1 | Q2 | Q3 | Q4
Planning / Design Step 1 Masterplanning (Project No. 2003-023-00) | [16 empty] | 386779
HGMP Development (Project No. 2003-005-00) | [16 empty] | 39400
TOTALS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Notes and Assumptions:
Planning / Design, Construction, Operations and Maintenance, Monitoring and Evaluation
Description | Month | [11 empty] | Quarter |  |  |  | FY 2004 | FY 2005 | FY 2006 | FY 2007 | FY 2008 | FY 2009 | FY 2010 | FY 2011 | FY 2012 | FY 2013
| January | February | March | April | May | June | July | August | September | October | November | December | Q1 | Q2 | Q3 | Q4
Planning / Design
Step 2: NEPA Etc, | [17 empty] | 150000 | 425000
Step 3: Final Design | [19 empty] | 2400000
Construction | [20 empty] | 10422000 | 6948000 |  |  |  |  | 17370000 | 17370000 |  |  | 17370000
Program Operations and Maintenance | 74016.5578 | 73933.2248 | 75853.2248 | 50366.9045 | 56362.5216 | 57362.5216 | 57362.5216 | 55562.5216 | 80812.5216 | 77780.9045 | 99183.2248 | 99183.2248 | 223803.0075 | 164091.9478 | 193737.5649 | 276147.3542 |  |  |  |  | 85777.9874 | 88694.439 | 917824.4655 | 949030.4974 | 981297.5343 | 1014661.6504
Monitoring and Evaluation | [12 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 162292.41 | 241712.1 | 241712.1 | 369182.7743 | 381734.9886 | 394713.9782 |  |  | Need Keith's ## | 316487.6
Capital Equipment for OM and ME | [21 empty] | 350386.8 | 233591.2
TOTALS | 74016.5578 | 73933.2248 | 75853.2248 | 50366.9045 | 56362.5216 | 57362.5216 | 57362.5216 | 55562.5216 | 80812.5216 | 77780.9045 | 99183.2248 | 99183.2248 | 223803.0075 | 164091.9478 | 193737.5649 | 276147.3542 | 0 | 150000 | 425000 | 2400000 | 10670070.3974 | 7628793.339 | 1393127.7655 | 1318213.2716 | 1363032.5229 | 1409375.6286
Notes and Assumptions;
All figures are based on 2004 dollars and projected from that point
[16 empty] | Check | 857779.8743 | 1.034 | 1.034 | 1.034 | 1.034 | 1.034 | 1.034 | 1.034 | 1.034 | 1.034
Related Research Programs
Description | Month | [11 empty] | Quarter |  |  |  | FY 2004 | FY 2005 | FY 2006 | FY 2007 | FY 2008 | FY 2009 | FY 2010 | FY 2011 | FY 2012 | FY 2013
| January | February | March | April | May | June | July | August | September | October | November | December | Q1 | Q2 | Q3 | Q4
Broodstock Testing and Collection Plan | [19 empty] | 495950 | [8 empty] | OK w/ MBI
Research to Assess Behavior of Adults Upstream of Wells Dam | [18 empty] | 397300 | [9 empty] | Need Steve's Eval of Bioanalysts
TOTALS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397300 | 495950 | 0 | 0 | 0 | 0 | 0 | 0
Notes and Assumptions
All figures are based on 2004 dollars

## APP_B_Cost_Sum_SpringAdd
Appendix B: Future Cost Summaries, Summer/ Fall and Spring Chinook Addition
Costs Expended to Date
| Description | Month | [11 empty] | Quarter |  |  |  | FY 2003
|  | January | February | March | April | May | June | July | August | September | October | November | December | Q1 | Q2 | Q3 | Q4 | Total | Total | Total | Total | Total | Total | Total | Total | Total | Total
| Planning / Design Step 1 Masterplanning | [16 empty] | 386779
| HGMP Development | [16 empty] | 39400
| TOTALS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Notes and Assumptions:
Figures shown are actual contracted funds from BPA
Planning / Design, Construction, Operations and Maintenance, Monitoring and Evaluation
| Description | Month | [11 empty] | Quarter |  |  |  | FY 2004 | FY 2005 | FY 2006 | FY 2007 | FY 2008 | FY 2009 | FY 2010 | FY 2011 | FY 2012 | FY 2013
|  | January | February | March | April | May | June | July | August | September | October | November | December | Q1 | Q2 | Q3 | Q4 | Total 0 | Total | Total | Total | Total | Total | Total | Total | Total | Total
Planning / Design
| Step 2: NEPA Etc, | [17 empty] | 150000 | 425000
| Step 3: Final Design | [19 empty] | 2400000
| Construction | [20 empty] | 13764239.4 | 9176159.6 |  |  |  |  | 22940399
| Program Operations and Maintenance | 90480.4359 | 90397.1029 | 92317.1029 | 63101.1328 | 69126.7499 | 70126.7499 | 70126.7499 | 68326.7499 | 106076.7499 | 103045.1328 | 128147.1029 | 128147.1029 | 273194.6417 | 202354.6327 | 244530.2498 | 359339.3386 |  |  |  |  | 86353.509 | 89289.5283 | 1154978.1832 | 1194247.4414 | 1234851.8544 | 1276836.8174 | 17370380
| Monitoring and Evaluation | [12 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 76217.8226 | 162165.58 | 162165.58 |  |  |  | 5570019 | 161998
| TOTALS | 90480.4359 | 90397.1029 | 92317.1029 | 63101.1328 | 69126.7499 | 70126.7499 | 70126.7499 | 68326.7499 | 106076.7499 | 103045.1328 | 128147.1029 | 128147.1029 | 273194.6417 | 202354.6327 | 244530.2498 | 359339.3386 | 0 | 150000 | 425000 | 2400000 | 13926810.7316 | 9427614.7083 | 1317143.7632 | 1194247.4414 | 1234851.8544 | 1276836.8174
Notes and Assumptions;
All figures are based on 2004 dollars and projected from that point
[17 empty] | Check | 1079418.8628 | 1.034 | 1.034 | 1.034 | 1.034 | 1.034 | 1.034 | 1.034 | 1.034 | 1.034
Related Research Programs
| Description | Month | [11 empty] | Quarter |  |  |  | FY 2004 | FY 2005 | FY 2006 | FY 2007 | FY 2008 | FY 2009 | FY 2010 | FY 2011 | FY 2012 | FY 2013
|  | January | February | March | April | May | June | July | August | September | October | November | December | Q1 | Q2 | Q3 | Q4 | Total 0 | Total | Total | Total | Total | Total | Total | Total | Total | Total
Broodstock Testing and Collection Plan
Research to Assess Behavior of Adults Upstream of Wells Dam
| TOTALS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0