## Sheet1
PER UNIT
| No. of Units | No. of Meetings | Meeting Duration (hrs) | Prep/Review per Meeting (hrs) | Total (hrs) | Notes
Cross-Cutting | 1 | 1 | 2 | 2 | 4 | Review of framework documents, including XYZ
Existing Market Model Review | 4
Method Review |  | 2 | 1 | 2 | 6 | Assumes two meetings, plus review time. Assumes more material model. Estimate may be higher for more complex model.
Model Review |  | 6 | 1.5 | 1 | 15 | Assumes 90 minute minutes every two weeks for a 3 month period plus minimal review time
Judgment |  | 1 | 2 | 1 | 3 | Assumes limited review required by those following along
Total |  | 9 |  |  | 24
Standards Review | 6 |  |  |  | 16 | Assumes approximately 1/2 to 2/3 the lift per standard compared to technology/market model review
Potential Future Model Development | 2 | (per model estimate)
Method Review |  | 3 | 2 | 2 | 12 | Assumes bigger lift for digging into complex model
Model Review |  | 6 | 1.5 | 2 | 21 | Assumes bigger lift for digging into complex model
Judgment |  | 1 | 2 | 1 | 3 | Assumes similar lift as other models
Total |  | 10 |  |  | 36
2016 Hours Estimate
Resource Lift by Person | Annual | Percent of Annual Hours | Notes
Primary Contract Analyst | 238 | 11.44% | Assumes familiarity of work (i.e. low-end of estiamte), working on all models, plus 1 hour for meeting prep
Cross Cutting | 4
Existing Models | 132
Standards | 102
Subcommittee Participate (full review) | 196 | 9.423% | Assumes review of all models
Subcommittee Participant (partial review) | 125 | 6.01% | Assumes detailed review on a subset of models plus 8 hrs of lift for other models (for review and participation in "Judgement" call
Additional RTF Staff Lift | 296 | 8.462%
Cross Cutting | 16 |  | Assumes all secondary contract analyst review cross cutting materials
Internal Team Review | 144 |  | Assume 1/2 hour for internal discussion per meeting (per secondary contract analyst)
Model Review | 24 |  | Assumes review of 1 model by secondary contract analyst
RTF Manager | 112 | 5.385% | Assumes monitoring of work, participating in meetings, plus cross cutting review
2017 Hours Estimate
Resource Lift by Person | Annual | Percent of Annual Hours | Notes
Primary Contract Analyst | 293 | 14.09% | Similar assumptions as for 2016, with the addition of 2 new models and no cross cutting review
Cross Cutting | 0
Existing Models | 99
Standards | 102
New Models | 92
Subcommittee Participate (full review) | 240 | 11.54% | Assumes review of all models, no cross cutting review, plus new models
Subcommittee Participant (partial review) | 157 | 7.548% | Assumes detailed review on a subset of models plus 8 hrs of lift for other models (for review and participation in "Judgement" call), plus 1 new model
Additional RTF Staff Lift | 328.5 | 10.6%
Cross Cutting | 8 |  | Assumes some refresher of cross cutting
Internal Team Review | 136 |  | Assume 1/2 hour for internal discussion per meeting (per secondary contract analyst), counts additional meetings for new models
Model Review | 60 |  | Assumes review of 2 models (one new, one existing) by secondary contract analyst
RTF Manager | 124.5 | 5.986% | Assumes monitoring of work, participating in meetings, plus cross cutting review